## Slide 1
SOFTWARE PROJECT ESTIMATE
MANAGEMENT APPROVAL
TOTAL ESTIMATE
€129K
incl. 15% contingency
DELIVERY
14 Weeks
approval to go-live
EFFORT
140 Days
estimated team effort
DECISION REQUIRED
Approve €129K budget
Authorize development & implementation
ESTIMATE BREAKDOWN
Workstream | Effort | Estimate
Requirements & Solution Design | 15 days | €12K
Application Development | 65 days | €52K
Integration / APIs | 25 days | €20K
Testing & UAT Support | 25 days | €20K
Deployment & Hypercare | 10 days | €8K
Contingency (15%) | — | €17K
DELIVERY PLAN
Req.
2w
Design
2w
Build
6w
Test/UAT
3w
Go-Live
1w
• Resource plan: PM • BA • 2 Developers • QA • DevOps support
• Assumption: existing infrastructure will be reused
• Assumption: business SMEs are available for UAT
• Risk: scope change or third-party integration may affect estimate
Approval requested: proceed with detailed planning, development and implementation within the approved €129K envelope.