## Slide 1
SOFTWARE PROJECT ESTIMATE • FOR MANAGEMENT APPROVAL
Order Management Platform Upgrade
Rana Das | Head of Engineering & AI Strategy, Liquid Alternatives | 21 Sep 2026
TOTAL EFFORT
612 p-days
DURATION
22 weeks
TOTAL COST
€486K
GO-LIVE
Mar 2027
TEAM PEAK
6 FTE
ESTIMATE BY PHASE
Phase | Days | Wks | Cost (€)
Discovery & Design | 64 | 3 | 48,000
Core Platform Build | 260 | 9 | 205,000
Integration (NAV/Recon) | 120 | 5 | 94,000
Test & QA Hardening | 96 | 4 | 74,000
UAT & Cut-over | 48 | 3 | 39,000
Hypercare (post go-live) | 24 | 2 | 26,000
Total | 612 | 22 | 486,000
TIMELINE (22 WEEKS)
Discovery
Build
Integration
Test/QA
UAT
Wk 0
Wk 22
TOP RISKS
Legacy mainframe feed format undocumented
High
NAV team availability for integration testing
Medium
Regulatory sign-off timeline (change mgmt)
High
COST BREAKDOWN
Chart: 
| Base estimate | Contingency (15%)
Cost | 423 | 63
ASK: Approve €486K & 6 FTE for 22 weeks | NEXT: Discovery sprint 0 within 5 business days of sign-off