SOFTWARE PROJECT
ESTIMATION HANDBOOK

A practical guide for estimating projects from discovery to production

Purpose Use this handbook when requirements are incomplete, architecture is not yet defined, and epics or stories do not exist. It provides a defensible way to estimate uncertainty, size, delivery effort and confidence without creating false precision.

Version 1.0

# How to Use This Handbook

The core principle is progressive elaboration: estimate at the level of detail that actually exists, then refine the estimate as requirements, architecture, epics, stories and delivery data become available.

In discovery, estimate capabilities, complexity, assumptions, dependencies and uncertainty.

When architecture emerges, add components, integrations, data, security and non-functional requirements.

When epics exist, estimate epics and cross-team dependencies.

When stories exist, use team-level delivery metrics such as throughput or velocity.

Once delivery starts, replace opinion-based estimates with evidence from actual delivery performance.

## Estimation Principles

| Principle | Application |
| --- | --- |
| Estimate what is known | Do not invent story-level precision when only capability-level information exists. |
| Use ranges | A range communicates uncertainty more honestly than a single date or effort number. |
| Separate effort from duration | Ten person-months of effort is not automatically ten months of calendar time. |
| Make assumptions visible | An estimate without assumptions is difficult to govern and easy to misuse. |
| Track confidence | An estimate should have a confidence level that improves as uncertainty reduces. |
| Re-estimate at gates | Refresh estimates after material changes in scope, architecture, team structure or risk. |
| Prefer evidence over opinion | As delivery progresses, use actual throughput, cycle time, defect and readiness data. |

Key warning The first rough estimate often becomes an unofficial commitment. Always label early estimates as Rough Order of Magnitude (ROM), include assumptions, state the confidence level, and specify when the estimate will be revisited.

# 1. Estimation Across the Project Lifecycle

| Stage | What to Estimate | Useful Metrics | Typical Confidence |
| --- | --- | --- | --- |
| 1. Discovery / Concept | Capabilities, workstreams, complexity bands, assumptions, unknowns | ROM range, team-months, confidence | Low |
| 2. Requirements Forming | Feature groups, actors, business rules, interfaces, data domains | Refined ROM | Low-Medium |
| 3. Architecture / Design | Components, services, integrations, NFRs, environments, migration | Bottom-up workstream estimate | Medium |
| 4. Epics Defined | Epics, dependencies, release slices, team ownership | Epic effort + capacity | Medium |
| 5. Stories Refined | Stories, acceptance criteria, technical tasks | Throughput / story points / cycle time | Medium-High |
| 6. Build & Test | Remaining scope, defects, automation, test completion | Forecast to complete | High |
| 7. Production Readiness | Defects, performance, security, support, rollback, operational readiness | Release readiness forecast | High |

# 2. Metrics to Use Before Epics and Stories Exist

## 2.1 Functional Capability Size

Create a capability map rather than a backlog. A capability is a meaningful business or system outcome such as authentication, reporting, workflow, search, notifications or administration.

| Capability | Complexity | Primary Drivers | Notes / Unknowns |
| --- | --- | --- | --- |
| Identity & access | M | SSO, roles, permissions | Identity provider assumed available |
| Workflow / approvals | L | Rules, state transitions, audit | Approval matrix not finalized |
| Reporting | M | Dashboards, exports, permissions | Volume and latency unknown |
| Notifications | S | Email / in-app events | SMS out of scope |
| Administration | M | Configuration, support tools | Operating model TBD |

Suggested scale: S = straightforward; M = moderate; L = complex; XL = highly complex or materially uncertain.

## 2.2 Integration Complexity

Integrations are frequently underestimated. Track the number, ownership, protocol, data direction, availability and uncertainty of each interface.

| Integration Type | Typical Complexity | Questions to Ask | Risk Indicators | Metric |
| --- | --- | --- | --- | --- |
| Existing internal REST API | Low-Medium | Is it documented and stable? | Rate limits, auth changes | Count + complexity |
| New internal interface | Medium | Who builds both ends? | Other-team dependency | Count + dependency |
| Legacy / mainframe | High | Batch? proprietary? test environment? | Limited expertise | High-risk integration count |
| External vendor | Medium-High | SLA? sandbox? support? | Contract / lead time | Vendor dependency count |
| Event / streaming | Medium-High | Ordering? replay? idempotency? | Operational complexity | Event flow count |

## 2.3 Data Complexity

Number of source systems and target systems

Number of major data domains / entities

Data volume and growth

Historical migration period

Data cleansing and reconciliation requirements

Retention, archival and deletion requirements

Master-data or reference-data dependencies

PII / sensitive-data handling

Reporting and analytics requirements

## 2.4 Non-Functional Requirements (NFRs)

| NFR Area | Low Complexity | High Complexity Indicator | Current Rating |
| --- | --- | --- | --- |
| Availability | Business-hours service | 24x7, multi-region, strict SLA | Unknown |
| Performance | Normal interactive use | High transaction rate / low latency | Unknown |
| Scalability | Predictable user base | Rapid or highly variable growth | Unknown |
| Security | Standard enterprise controls | Privileged workflows / sensitive data | Unknown |
| Audit | Basic logs | Regulated immutable audit trail | Unknown |
| Disaster Recovery | Restore from backups | Tight RTO / RPO | Unknown |
| Accessibility | Standard web accessibility | Strict regulatory / multi-channel | Unknown |
| Observability | Standard monitoring | Distributed tracing / complex SLOs | Unknown |

## 2.5 Technical Uncertainty

Treat uncertainty as a first-class metric. Unknowns should not disappear inside estimates; they should be recorded and driven down.

| Area | Example Rating | Typical Evidence Needed to Reduce Uncertainty |
| --- | --- | --- |
| Requirements | High | Approved scope, process maps, business rules |
| Architecture | High | Target architecture and technology choices |
| Integrations | Medium-High | Interface contracts and environment access |
| Data migration | High | Profiling, mapping and volume analysis |
| Security | Medium | Threat model, control requirements, approvals |
| Infrastructure | Medium | Hosting pattern, environments, network dependencies |

## 2.6 Assumptions, Unknowns and Dependencies

Assumptions: statements currently treated as true for estimation.

Unknowns: information not yet available that could materially change effort or duration.

Dependencies: people, teams, suppliers, systems or approvals required to proceed.

Constraints: fixed dates, technologies, regulations, budgets or operational limits.

Good early-stage dashboard Show: capability count by complexity; number of integrations; high-risk integrations; number of data sources; NFR ratings; major assumptions; major unknowns; critical dependencies; estimate range; uncertainty reserve; and estimate confidence.

# 3. A Simple Complexity Scoring Model

A lightweight score can help compare projects before detailed estimates exist. This is not a substitute for engineering judgement; it is a consistency mechanism.

| Dimension | 1 - Low | 2 - Moderate | 3 - High | Weight (example) |
| --- | --- | --- | --- | --- |
| Functional complexity | Few simple capabilities | Multiple workflows | Complex rules / many actors | 25% |
| Integrations | 0-2 stable | 3-5 mixed | 6+ or legacy/vendor-heavy | 20% |
| Data | Simple CRUD | Migration/reporting | Large/dirty/regulatory data | 15% |
| NFRs | Standard | Some strict NFRs | High availability/security/performance | 15% |
| Technical novelty | Known stack | Some new patterns | New platform/architecture | 10% |
| Dependencies | Mostly internal | Several teams | Critical vendors / approvals | 10% |
| Requirements uncertainty | Low | Medium | High | 5% |

Example interpretation: weighted score near 1.0 = low complexity; around 2.0 = moderate; approaching 3.0 = high complexity. Use the score to calibrate ranges and contingency, not to generate a fake exact duration.

# 4. Estimating Effort and Duration

## 4.1 Use Team-Months for Early ROMs

When work is not decomposed into stories, team-months or workstream-months are usually more defensible than detailed hours.

Example Current ROM: 35-50 person-months of engineering effort, expected to require approximately 7-10 calendar months with the assumed team shape. The range excludes major scope expansion and depends on the integration and migration assumptions listed in the estimate.

## 4.2 Do Not Confuse Effort with Calendar Time

Some activities can run in parallel; others are sequential.

Adding people does not linearly reduce duration.

Specialist bottlenecks can dominate the critical path.

Approval, vendor and environment lead times add elapsed time but not necessarily engineering effort.

Team ramp-up, onboarding and coordination overhead should be reflected in duration.

## 4.3 Use Three-Point Estimates

For uncertain workstreams, record optimistic (O), most likely (M) and pessimistic (P) estimates. A simple expected value is (O + 4M + P) / 6.

| Workstream | Optimistic | Most Likely | Pessimistic | Notes |
| --- | --- | --- | --- | --- |
| Core application | 4 mo | 6 mo | 8 mo | Depends on workflow complexity |
| Integrations | 2 mo | 3 mo | 5 mo | Vendor API maturity unknown |
| Migration | 1 mo | 2 mo | 4 mo | Data quality not profiled |
| Hardening & release | 1 mo | 1.5 mo | 2 mo | Performance scope TBD |

# 5. Contingency and Uncertainty Reserve

Contingency should reflect known uncertainty. It should be visible, governed and reduced as uncertainty is retired.

| Project Maturity | Indicative Reserve | When It May Be Appropriate |
| --- | --- | --- |
| Concept / discovery | 25-50% | Requirements and architecture largely unknown |
| Requirements baselined | 15-30% | Scope clearer but design / integration detail incomplete |
| Architecture + epics defined | 10-20% | Major technical approach and workstreams understood |
| Delivery underway | 5-15% | Actual throughput and remaining scope available |

These ranges are planning heuristics, not universal standards. Calibrate them to your organisation and project risk profile.

# 6. Estimate Confidence

Confidence describes how stable the estimate is likely to be if current assumptions hold. It is better communicated as a band or narrative than as a precise mathematical probability.

| Confidence | Typical Situation | Estimate Form | Recommended Language |
| --- | --- | --- | --- |
| Low | Scope/design largely unknown | Wide ROM range | Directional estimate; substantial change expected |
| Low-Medium | Requirements forming | Refined ROM | Major drivers known; material uncertainty remains |
| Medium | Architecture and epics available | Workstream / epic estimate | Reasonable planning baseline |
| Medium-High | Stories refined and team stable | Delivery forecast | Supported by delivery evidence |
| High | Late delivery / release readiness | Forecast to completion | Remaining uncertainty is limited |

# 7. Re-Estimation Gates

Requirements baseline approved

Target architecture agreed

Major integrations identified and validated

Data profiling completed

Security / compliance requirements confirmed

Epics created and sized

Delivery teams staffed

First 3-4 sprints completed

Major scope change approved

Material dependency or vendor change

Pre-production readiness review

Rule of thumb Re-estimate when the information set changes materially, not merely because a calendar milestone has passed.

# 8. Metrics Once Delivery Starts

| Metric | What It Tells You | Useful For | Watch Out For |
| --- | --- | --- | --- |
| Throughput | Items completed per period | Forecasting remaining work | Requires reasonably consistent item size |
| Cycle time | Time from start to done | Flow and predictability | Segment by work type |
| Velocity | Story points completed | Team-specific sprint planning | Do not compare teams |
| Burn-up | Scope completed vs total scope | Scope change + progress | Needs maintained backlog |
| Defect arrival / closure | Quality trend | Testing and release forecast | Severity matters |
| Automated test coverage | Regression capability | Quality signal | Coverage alone does not prove quality |
| Blocked time | Dependency friction | Delivery risk | Track cause, not just count |
| Release readiness | Operational completion | Go-live decision | Use objective exit criteria |

# 9. Production Readiness Metrics

| Readiness Area | Example Exit Criterion |
| --- | --- |
| Functional completion | Critical scope complete; deferred items documented |
| Defect position | No unresolved release-blocking defects; severity trend acceptable |
| Performance | Load / response targets met |
| Security | Required reviews, scans and remediation complete |
| Resilience | Backup, restore, failover and recovery procedures validated |
| Observability | Logging, metrics, alerts and dashboards operational |
| Support | Runbooks, support model and ownership agreed |
| Deployment | Release / rollback procedures rehearsed |
| Data migration | Reconciliation and cutover validation complete |
| Business readiness | Training, communications and operational procedures complete |

# 10. Reusable Templates

## 10.1 Early-Stage ROM Estimate Template

| Project / Initiative |  |
| --- | --- |
| Estimate Date |  |
| Estimate Type | ROM / Refined ROM / Delivery Forecast |
| Current Stage |  |
| Scope Summary |  |
| Out of Scope |  |
| Assumed Team Shape |  |
| Estimated Effort |  |
| Estimated Duration Range |  |
| Confidence | Low / Low-Medium / Medium / Medium-High / High |
| Uncertainty Reserve |  |
| Top 5 Assumptions |  |
| Top 5 Unknowns |  |
| Critical Dependencies |  |
| Highest-Risk Areas |  |
| Next Re-estimation Gate |  |

## 10.2 Assumption Log

| ID | Assumption | Impact if False | Owner | Validation Date |
| --- | --- | --- | --- | --- |

## 10.3 Unknown / Decision Log

| ID | Unknown / Decision Needed | Estimate Impact | Owner | Target Date |
| --- | --- | --- | --- | --- |

## 10.4 Dependency Register

| Dependency | Owner | Needed By | Critical? | Status | Estimate Impact |
| --- | --- | --- | --- | --- | --- |

## 10.5 Capability Sizing Sheet

| Capability | S/M/L/XL | Integration | Data | NFR | Comments |
| --- | --- | --- | --- | --- | --- |

# 11. Estimation Workshop Checklist

## Before the Workshop

Gather current scope, process maps, concept notes and business objectives.

Identify product, architecture, engineering, QA, data, security and operations representatives.

List known external systems, vendors, data sources and delivery constraints.

Prepare an assumption log and capability list.

## During the Workshop

Confirm the estimate purpose: funding, roadmap, staffing, sequencing or release planning.

Separate must-have scope from optional scope.

Size capabilities using the same scale and criteria.

Score integration, data and NFR complexity.

Record assumptions and unknowns as they arise.

Identify critical-path dependencies and specialist bottlenecks.

Create optimistic, likely and pessimistic scenarios.

Agree the confidence level and next re-estimation gate.

## After the Workshop

Publish the estimate together with assumptions and exclusions.

Make uncertainty visible instead of hiding it inside a single number.

Assign owners to validate major unknowns.

Schedule re-estimation at the next information maturity gate.

Track estimate changes and explain what new information caused them.

# 12. Common Estimation Anti-Patterns

| Anti-Pattern | Why It Fails |
| --- | --- |
| False precision | Giving exact hours or dates when requirements and design are immature. |
| Premature story points | Inventing stories solely to create a number. |
| Single-number estimates | Removing uncertainty from the conversation. |
| Hidden assumptions | Publishing effort without stating what must be true. |
| Ignoring NFRs | Estimating features while omitting security, performance, resilience and operations. |
| Ignoring dependency lead time | Counting engineering effort but not vendor, environment or approval delays. |
| Treating contingency as padding | Using reserve without linking it to specific uncertainty. |
| Comparing team velocity | Using story points as an organisation-wide productivity metric. |
| Never re-estimating | Treating an early ROM as permanent despite new information. |

# 13. Worked Example: Project in Infancy

Scenario: A new internal workflow platform is proposed. Business requirements are still being written, architecture is undecided, and no epics or user stories exist.

| Metric | Observation | Estimation Interpretation |
| --- | --- | --- |
| Capabilities | 9 identified; 2 large, 5 medium, 2 small | Moderate-high functional scope |
| Integrations | 6; one legacy, two vendor | Integration risk is material |
| Data | 3 sources; migration required | Migration estimate remains wide |
| NFRs | Security high; performance unknown | Architecture work required before refinement |
| Dependencies | 4 critical external teams | Calendar duration may exceed pure effort |
| Unknowns | 11 material unknowns | Confidence remains low |
| Estimate | 40-60 person-months | Use range, not exact hours |
| Duration | 8-12 months | Assumes stable 7-9 person cross-functional team |
| Reserve | 30% | Reflects requirement, architecture and migration uncertainty |
| Confidence | Low | Re-estimate after requirements and architecture baseline |

## Suggested Estimate Statement

ROM wording This is a Rough Order of Magnitude estimate based on the current understanding of scope. Requirements, architecture, integration complexity, data migration and non-functional requirements are still being developed. The estimate is therefore presented as a range and includes an explicit uncertainty reserve. It should not be treated as a delivery commitment. The estimate will be refreshed after requirements and target architecture are baselined.

# 14. One-Page Reference

| If You Have... | Estimate Using... | Avoid... |
| --- | --- | --- |
| Only an idea / concept | Capabilities, complexity, assumptions, dependencies, ROM range | Hours and story points |
| Requirements but no design | Feature groups, integration/data/NFR analysis, workstreams | Single-date commitments |
| Architecture + epics | Epic/workstream effort, dependency sequencing, capacity | Ignoring lead times |
| Stories + stable team | Throughput, cycle time, velocity, burn-up | Cross-team velocity comparisons |
| Active delivery | Actual completion rate, scope trend, defect trend | Forecasting only from original estimate |
| Pre-production | Readiness criteria, blockers, residual defects, operational checks | Equating code complete with production ready |

Five numbers worth showing on every estimate 1) effort range; 2) duration range; 3) confidence; 4) uncertainty reserve; 5) number of material assumptions / unknowns.

# 15. Final Guidance

A good estimate is not the most detailed estimate. It is the estimate that accurately reflects the information available at the time, makes uncertainty visible, and becomes more precise as evidence improves. Early in a project, the objective is not to predict an exact finish date; it is to establish a credible planning range, identify the biggest drivers of uncertainty, and define what information is needed to improve the forecast.